## Milestones
Items | Owner | 2024-08-20 | 2024-08-27 | 2024-09-03 | 2024-09-10 | 2024-09-17 | 2024-09-24 | 2024-10-01 | 2024-10-08 | 2024-10-15 | 2024-10-22 | 2024-10-29 | 2024-11-05 | 2024-11-12 | 2024-11-19 | 2024-11-26 | 2024-12-03
Research | All
Define Individual Sub-Systems | All | [9 empty] | Not Started
Make a list of parts (BOM) | Alex | [9 empty] | In Progress
Determine IDE and SDK | Vlad | [9 empty] | Completed
Download IDE and SDK | Vlad | [9 empty] | Behind Schedule
Creation of all Website Urls | Vlad
Concept of Operations | All
Sub-System Introduction | All
FSR, ICD, Milestones, and Validation Plan | All
Order specified parts | Alex, Juan
Signup/Login/Logout Operations | Vlad
Midterm Presentation | All
Homepage HTML Layout | Vlad
Band Field HTML Layout (Director/Marcher) | Vlad
Design receiver and transmitter PCBs | Alex
Successfully program transmitter and receiver communication | Juan
Calculate position from each transmitter relative to the receiver | Juan
Order first design of PCB | Alex
Update Presentation | All
Store and Retrieve Location Data Internally | Vlad
Map out the location of the transmitters | Juan
Learn to Solder PCBs | Alex
Test PCB Soldering | Alex
Re-solder and Retest if Need be | Alex
Retrive Location Data Externally (Recordings) | Vlad
Program delivery of positional data via WiFi | Juan
Minor Web Style Adjustments | Vlad
Upload finished code | Juan
Network between devices through WiFi | Vlad
Verify Demo Testing for PCB | Alex
Final Presentation | All
Final Demo | All
Final Report | All

## Milestone404
Items | Owner | 2025-01-27 | 2025-02-03 | 2025-02-10 | 2025-02-17 | 2025-02-24 | 2025-03-03 | 2025-03-10 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-04-28
Redesign Board and Order New Parts and Board | Alex
Bi-Weekly Update #1 | Both | [9 empty] | Not Started
Use Arduino to Create Firmware | Vlad | [9 empty] | In Progress
Finalize Arduino Details | Both | [9 empty] | Completed
Solder New Boards and Test | Alex | [9 empty] | Behind Schedule
Test Arduino Code Implementation | Alex
Bi-Weekly Update #2 | Both
Make Changes to Code for Hardware Implementation | Alex
Finalize Website Subsystem | Vlad
Bi-Weekly Update #3 | Both
Test Website Connectivity | Vlad
Finalize Integration | Both
Test Range of Detection | Both
Test Precision of Detection | Both
Spring Break (If needed, catch up if behind) | Both
Bi-Weekly Update #4 | Both
Participate in Design Blitz | Both
Implement Design Changes if Needed | Both
Bi-Weekly Update #5 | Both
Work on Physical Casing | Alex
Test Physical Properties (Thermal, Weight, etc) | Alex
Final Presentation | Both
Final Demo | Both
Final Report | Both

## Validation
Paragraph # | Test Name | Success Criteria | Methodology | Status | Owner(s)
3.2.1.1 | Location Precision | The Marching Band LPS will be able to provide the location of each marcher with an accuracy of +/- 1 meter. | Establish reference points with known positions and compare LPS data to calculate the precision error. | Tested: Success. Tag was walked around and then its transmitted x and y were compared against real x and y | Full Team
3.2.1.2 | Range of Detection | The Marching Band LPS will be able to detect marchers within a football field with the dimensions of 100 meters by 50 meters. | Move around a transmitter at the edges of the football field to ensure stable connection. | Tested: Tag was walked across field and maintained transmission at all four corners. | Full Team
3.2.1.3 | Website Data Process Time | Location data will be processed and displayed on the website associated with the Marching Band LPS in one second or less. | Add a timer on the display and count the time it takes to process 50 location coordinates. | Tested: Success. Connected to website and confirmed over 50 data logs in under 50 seconds (47 seconds) | Full Team
3.2.1.4 | Website Connection | The website will connect through WiFi to the receivers. | Be able to network through a local connection like a hotspot from one device on the python project. | Tested: Success. Connected to WiFi and displayed successul connection message | Vlad Lebedev
3.2.2.1 | Mass | The total mass of the PCB and additional hardware will not exceed 1kg. | Measure mass of the hardware with a digital scale. | Tested: Success. The total mass weighed in at 0.0635 kg. | Alex Flores
3.2.2.2 | Volume Envelope | The housing unit for the PCB will not exceed the dimensions of 80 x 80 x 160 mm. | Perform measurements on the hardware to ensure it fits into specified dimensions | Tested: Success. The dimensions measured are 80 x 40 x 80 mm. | Full Team
3.2.2.3 | Receiver Mounting | The receiver can be mounted onto a pole similar in scale to that of a speaker stand. The transmitter can be mounted comfortable onto a person | The receiver will be mounted onto a stand and shaken lightly to ensure stability. The transmitter will be worn by and individual who will move to test comfortability | Tested: Success. Casing was mounted to a PVC pipe and shaken to ensure stability and was mounted to a person to ensure comfort | Full Team
3.2.3.1.1 | Power Consumption | The maximum peak power of the system shall not exceed 2 watt hours | Use mulitmeter to validate watt hours for the device | Tested: Success. Totally draw required is 0.78 Wh when adding up current draw from various parts | Alex Flores
3.2.3.1.2 | Input Voltage Level | The input voltage level for the Marching Band LPS shall be within 3.0V- 3.5V. | Use mulitmeter to validate input voltage levels | Tested: Success. Output is 3.25V | Alex Flores
3.2.4.2 | Thermal | The system should be operational in environments that have temperatures within the range of 10°F and 120°F | System will be placed in a heating device and cooling device and be monitored to guarantee operation in the respective conditions. | Tested: Success. Heat was simulated by an oven. Cooling was simulated by being placed in a freezer | Alex Flores